# Eastbourne Site Software Development Procedure

CONTENTS

1	Objectives & Scope	2

1.1	Overview	2

1.1	Scope	2

2	Definitions	2

3	Responsibilities	2

4	Process	3

4.1	Process Description	3

4.1.1	Software Definition	4

4.1.2	Software Requirements Capture and Analysis	4

4.1.3	Software Design	4

4.1.4	Software Implementation	5

4.1.5	Software Verification & Testing	5

4.1.6	Software Deployment	6

4.1.7	Software Evaluation	8

4.1.8	Supporting and Related Processes	8

4.1.9	Mapping to Edwards Product Commercialisation Process	10

4.1.10	Project and Design Reviews	10

Measurement and Review	12

4.1.11	Measurement	12

4.1.12	Review	12

5	Support Documentation	12

Global Procedures	12

Local Eastbourne Procedures	13

Non-Edwards Documents	13

Document Templates	13

Form Templates	14

6	Change \ Review History	14

7	Record Retention	15

# Objectives & Scope

## Overview

This document defines the procedures to be followed at the Eastbourne Edwards site during the development of software, in order to ensure the quality and integrity of the software.

It provides detailed process requirements that confirm to the top level requirements mandated in EQE024 (reference 5.1.1) and the overall Edwards software development process defined by the Edwards Software Development Procedure (reference 5.1.2).

## Scope

It shall be applied to all software development where the software is to be supplied in or as a product to an External Customer.

# Definitions

Edwards Intranet – http://edweb/

External Customer – any organisation outside Edwards that uses Edwards products containing Edwards software.

EQE – Edwards Quality Element

External agents – Individuals and groups outside the software project team.  These may be Edwards Product Management Product Support and Service functions, or the overall project team if the software is part of a larger system.

NPI – New Product Introduction

PCP – [Edwards] Product Commercialisation Process

PRR – [Eastbourne bi-monthly] Project Resourcing Review

Software - Any code used to control or measure a process which is stored on any computer storage media including, but not restricted to, magnetic media or programmable devices.

Software Project File - The file (or files with an index) maintained with all project related documentation and quality records

# Responsibilities

Project Leader - The person defined as responsible for the software within the project. This person need not be the same as the overall project leader in the case of a multidisciplinary project. For a small project, this may be the software engineer.

Software Engineer - The engineer responsible for the development of the software.

Software Manager - The manager with the responsibility for the development of software proposed.

# Process

## Process Description

The Edwards Eastbourne software development process is iterative in nature, and covers the following steps for each iteration cycle of a project:

Definition (first iteration only);

Requirements Capture and Analysis;

Design;

Implementation;

Verification & Testing;

Deployment;

Evaluation.

The following diagram illustrates the sequence of these phases.

Design

Requirements Capture & Analysis

Implementation

Definition

Verification & Testing

Deployment

Evaluation

Alpha release

Beta release

Production release

Figure 1 - Software Process Diagram

Click on each arrow to go to the description of each phase. They are hyperlinks to the relevant sections in the document.  Phases in blue in the diagram above are managed by a project’s software development team.  Phases in purple are carried out by external agents, however, are still referred to within this procedure.

### Software Definition

This process is strictly outside the scope of this procedure but is included for completeness.  It represents the identification of the customer requirements by Edwards Product management, and System requirements by the overall project team if the software will be part of a larger system.  The top-level requirements are provided to the software development team at the start of the first project iteration as one or more written and approved documents, each with a version number and/or date.

Without defined requirements, any project will proceed at risk.

During the Definition phase, project inception/creation will occur (reference 5.1.10) As part of this process a project folder will be created on the local server.

### Software Requirements Capture and Analysis

This process is the compilation and translation of customer and system requirements (e.g. functional and performance requirements) into a coherent and consistent set of software requirements.  The outputs shall be:

- a ‘software requirements’ or ‘interface’ specification that defines the system’s behaviour;

- a project plan that defines the project’s stages.

For projects where an adequate customer or system requirements document exists (e.g.: a subsystem requirements specification), it is enough merely to provide a link to the supplied requirements document in the project’s Software\Requirements folder.

On subsequent product iterations, an up-issue to the software requirements or interface specification only needs to be produced if there are high level requirements changes identified by the preceding Evaluation phase.

A project plan shall be produced by the project leader or an appointed deputy. This shall:

- identify development and testing stages and their reviews;

- assign responsibilities and authorities for design and development;

- identify time and manpower requirements.

This plan should be maintained and updated through subsequent iterations.  Planning for projects that are themselves part of a larger project can be subsumed into overall planning for that larger project.

### Software Design

This process defines the software architecture (e.g. split of software functions between multi-modular hardware or software modules).  A detailed design should also be produced that defines the internal structure of the software, written in a manner that can be understood by other software engineers.  The design should be a natural derivative of the Software Requirement Specification and follow the same naming conventions.

For larger software systems (more than 80 person days of effort, or with teams of multiple software engineers), it may be necessary to produce separate high level (‘architectural’) and low level (‘detailed’) design documentation.

Use of reverse engineering tools to generate detailed design documentation after the implementation phase is permitted.

On the first product iteration, the high-level design must be reviewed by members of the software project team and approved by the Software Project Leader.  On time critical projects it is permitted (but discouraged) to start software implementation before the architectural design has been agreed and approved. If subsequent product iterations produce no change to the high-level design, then no update to the design may be needed.

Systems that rely on a high degree of architectural re-use from previous projects do not require a new high-level design document to be written.  This caveat shall be exercised at the discretion of the Software Project Leader.  In such cases, the re-used high level design document still needs to be reviewed.

It is recommended, but not mandated, that Unified Modelling Language (UML) notation (reference 5.3.1, OMG UML Specification v2.2) is used to describe the design in documentation.

One or more Software Verification Specifications shall also be produced during the first iteration and maintained during subsequent ones. The tests identified should be based upon the requirements and design specifications and should aim to prove that all requirements have been successfully implemented.

### Software Implementation

This process produces the machine-readable implementation of the design.  For executable binary code, compiled source code is produced.  Some systems will actually require interpreted source code and therefore not require compilation.  Coding standards to be used are identified in section 5, Support Documentation.

On larger systems (more than 80 person days of effort) a separate software integration sub-phase is recommended prior to commencement of Software Verification and Testing.

### Software Verification & Testing

Once implementation is completed, a baseline must be recorded (of at least alpha level).  Then the software will be tested using the Software Verification Specification.

Testing must be carried out against a recorded baseline version of the software   It is permitted to record the baseline by its build time and date, provided that all the source code used for the build is under configuration management at the time. (See reference 5.2.2, Software Configuration Management D&T.)

The results of the test will be recorded in a software verification or test report.  This will indicate the baseline version number of software tested, status of the tests, and any additional equipment used.

Subsequent project iterations do not need to re-run all of the tests in the Software Verification Specification, and will generally run a subset of the full list of verification tests in order to check existing functionality, plus a set of new tests for new functionality and fixes.

Certain products allow configurability via downloading or modification of parameters stored in files or non-volatile memory.  These sets of parameters need to be checked for compatibility with each new production software release.  The procedure to cover this checking is described in reference 5.1.11.

Independent testing of software by shall also occur wherever practicable.  This can be by other teams (Electronics, NPI, Production, Global Support, Global Systems Group) or groups on other sites (Edwards Hillsboro, Niagara, Japan, Korea.)  Examples of independent testing are: Pump controller software verification testing by Global Semicon Support Group or Pumps NPI Team; Integrated System Testing by Global Systems Group at Niagara; Turbo Instrument Controller Software Verification Testing by Electronics team. Records of such testing shall also be kept alongside, or as part of, the Software Verification Specification.

### Software Deployment

Once software verification and testing has been completed to the satisfaction of the project leader, the software may be released for use by customers as a beta or production baseline release.

Three levels of software baseline are defined

| Baseline level | Description | Status |
| --- | --- | --- |
| Alpha | The software has undergone no formal testing, and is therefore supplied for evaluation purposes only. | May only be used for testing and evaluation internally only within the Edwards organisation. |
| Beta | The software release has not yet been completely validated. (i.e.: It has not been formally accepted for use as a Production item.) | May be supplied to an external customer on the understanding that it is not supported by the Edwards Service Organisation. Beta releases of embedded software may be supplied for use in as part of trials on Edwards customer sites. Beta releases may be supplied to Edwards customers in limited numbers upon request for a non-standard order. |
| Production | The software has undergone full formal verification. It is assigned a unique MAPICS part code and version letter, starting at A. (see reference 5.2.2) | May be incorporated in or used as Edwards production items for purchase by external customers |

The process of creating, identifying and preparing a software baseline for release is described in reference 5.2.2 (Software Configuration Management D&T).

Production level ‘Embedded’ software releases included in products that go through product testing process(es) need to be checked independently (by another team/group) to see that the product hardware loaded with the new software release passes successfully through all such levels of product testing. (These may include ATE, PCA functional test and full product testing.)

For all production level software releases (apart from those of the product EdCentra’) an EC is raised by the Software Project Leader or appointed deputy to request introduction the new release into the manufacturing and production process.  Reference 5.1.7, describes the EC process itself.  Specific actions need to be included on the EC form on the Implementation sheet:

| Category | Action | Description | Responsibility |
| --- | --- | --- | --- |
| MAPICS | Item Masters / PCS | Update MAPICS to reflect the new software version. | Production Engineering Department |
| Documentation | Product / Instruction Manuals | (If needed) Update product instruction manual to reflect new functionality. | Software team |
| Documentation | SIB | Draft SIB describing release and pass to Service organisation for distribution. | Software team |
| Test Engineering | ATE Test software | (If needed) Update ATE software to use new software. | Test Engineering |
| Test Engineering | Functional Test software | (If needed) Update Functional test software to ensure compatibility. | Test Engineering |
| Test Engineering | Second site affected | (If needed) Inform representative of second site when hardware with new software loaded starts to be sent to them, so that they can update their production test software. | Production Engineering Department |
| Test Engineering | Software download | (If needed) Ensure new software is available for use by Service organisation and/or customers by making it available on global servers or dedicated customer service internet (product dependent). | Software team |
| Approvals | Copy Exact | Products for use by specific customers must be assessed against the copy exact process. (Reference 5.1.12) | Semicon Support Group |
| Software | Firmware - program | Copy new software to soft_rel$/Released share on Eastbourne server. | Software team |
| Software | Firmware - issue | Copy new software from soft_rel$/Released to soft_rel$/Master share on Eastbourne server. | Production Engineering Department |
| Cells | Serial Number(s) | Record serial number of first unit with new software. | Production Engineering Department |

Additionally, a copy of the software itself, a release note, and a list of the changes included, need to be added as a Pre-approval attachment on the header sheet.  Also a functional test report(s) (see section 4.1.5) need to be added as an attachment to the Verification sheet.

Reference 5.2.1 (D&T450, “Release of Firmware and Test Software to Production”) describes the process of introduction of embedded software into production after the EC has been authorised.

Reference 5.2.3 describes the roll-out process for network monitoring (EdCentra) software.

### Software Evaluation

This process is strictly outside the scope of this procedure but is included for completeness.  It covers customer use of the software once deployed, and feedback of the experience gained as a result.

Customer evaluation of existing released products may produce recommendations for updates from the Edwards Product Management, Product Support and Service functions, resulting in the need for another iteration of software.  These recommendations may be requests for new requirements or notification of defects in existing functionality.

Many Service and customer requests for change are received as non-conformances in FRACAS, as defined in procedure reference 5.1.6.  Problems identified and changes needed are noted by the software project team as “change requests” in the software configuration management system for each project. (See reference 5.2.2, Software Configuration Management D&T).

### Supporting and Related Processes

#### Configuration Management

All work products that are combined to build a software baseline version are kept in a configuration management system, see reference 5.2.2, Software Configuration Management D&T, for details.  This procedure also covers software “change requests”.

#### Location of software project documentation

The project folder structure is recommended, but not mandated, to be arranged as in the diagram that follows.

Figure 2 – Suggested Project Folder Structure

Software requirements and design documentation should be stored in the project’s Software Configuration Management system. However, it is strongly recommended that copies should be kept outside the Configuration Management system as well. Therefore Software requirements and design documentation should also be held in the “Technical” sub-folder of the overall project folder created at project Definition (reference 5.1.10).    Records of reviews and inspections shall also be kept there.

Software source code shall be stored in the project’s Software Configuration Management system (reference 5.2.2).

For each software build version, copies of images, related release notes and software test results for that version should be stored in a separate folder under “Released Versions”.

### Mapping to Edwards Product Commercialisation Process

Development and introduction of major new products is covered by a Product Commercialisation Process (“PCP”, reference 5.1.8) that ensures integration of the development process with other Edwards functions and its review.

On the first iteration of a major software project, the PCP needs to be followed.  The software development project lifecycle shall map onto the PCP stage gates as follows:

Design

Requirements Capture & Analysis

Implementation

Definition

Verification & Testing

Deployment

Evaluation

1

2

5

3

4

Beta release

Alpha release

Production release

Figure 3 – PCP Stage Gates to Software Process Mapping

(Click on each arrow to go to the description of each phase. They are hyperlinks to the relevant sections in the document.).

### Project and Design Reviews

If the overall project manager has identified that software development constitutes a risk for the project, software peer reviews will occur for the project.  Details of these software peer reviews are given in reference 5.1.9.  At each of the PCP stage gates, larger software projects require system design reviews to be held and details of these peer reviews are to be provided for each one.

On projects without software peer reviews, or projects that have proceeded to a subsequent iteration, at least the following reviews must occur during each iteration:

- Software Requirements Review 	(Stage Gate 3 - Requirements)

- Software Design Review 		(Stage Gate 3 - Design)

- Software Verification Review 	(Stage Gate 4 and/or 5* - Pre beta and/or Launch)

Design

Requirements Capture & Analysis

Implementation

Definition

Evaluation

Software Requirements Review

Software Design Review

Beta release

Verification & Testing

Software Verification Review

Deployment

Alpha release

Production release

Figure 4 – Software Reviews

* A Software Verification Review should be held before a beta software release is made that will be used by an external customer.  This corresponds with stage gate E-2 in the PCP.

Form templates are included in section 5.5 to record these meetings. Each form includes a checklist that must be completed at the time of the review meeting. (Click on the red circles to go to the template forms for each type of review. They are hyperlinks to the relevant templates.)

In addition, where necessary, regular scheduled formal meetings shall occur to agree which defect fixes and new features should be grouped together for a particular new release, and the timing of when that release should occur. Examples of such meetings are: monthly Semicon Pump & Steering Group meetings, monthly Management Quality Reviews (MQRs), monthly Projects & Resource Reviews (PRRs), and project specific reviews and meetings.

## Measurement and Review

### Measurement

The primary quality goal for software development at the Eastbourne site is to minimise the number of defects in delivered products.

#### Goals

The following sub-goals have therefore been defined:

1.  Reduce software defects in delivered product

2.  Improve software defect containment (prior to production release)

#### Metrics

The following metrics shall be gathered and maintained for Software Products.

- Total Change Requests reported in a month by Request Type and Priority - The number of reported Change Requests in the month.

Request Type can be ‘Bug’ or ‘Enhancement’.

- External Vs Internal Change Requests - Change Requests identified in Live code/will affect Live Code Vs Internal Change Requests. A Change Request raised as an internal one on analysis can be understood as one affecting Live code and, in this case, would be changed to an ‘External’ Change Request.

- Backlog by Age – The number of Open CRs distributed over time.

### Review

As a minimum, these figures shall be collated on a quarterly basis.  The Software Quality Engineer would review these metrics with respective Product Team Lead in cases where there are quality concerns, records are not sufficiently maintained or do not have all information. Improvement opportunities will be identified as part of the review process.

# Support Documentation

## Global Procedures

5.1.1	Software Quality

5.1.2	Software Quality Development Procedure

5.1.3	Software Quality Edwards C# Coding Standard

5.1.4	Software Quality C C++ Coding Standard

5.1.5	Software Quality Integrated System Software Design and Development Procedure

5.1.6	Software Quality Agile Process

5.1.7	Software Quality PLC Coding Standard

5.1.8	016-005, Global Corrective Action Process, Web-Based FRACAS NCR System

5.1.9	Q73-701, Engineering Change Process.  Web-Based EC system

5.1.10	Q71-101, Product Commercialisation Process (PCP)

5.1.11	Peer Review Process (part of Q71-101)

5.1.12	Project Files & TCF's (part of Q71-101)

5.1.13	QS24-101, Configuration compatibility test procedure

5.1.14	Q82-202, Copy Exact Compliance

## Local Eastbourne Procedures

5.2.1	D&T450, Release of Firmware and Test Software to Production

5.2.2	D&T212, Software Configuration Management

5.2.3	D&T622, EdCentra Software Release Process

## Non-Edwards Documents

5.3.1	OMG Unified Modeling Language™ (OMG UML

## Document Templates

| Software Requirements Specification |  |
| --- | --- |
| Interface Specification |  |
| Software Architecture Specification |  |
| Software Design Specification |  |
| Software Verification Specification (Word) |  |
| Software Verification Specification (Excel) |  |

## Form Templates

| Software Inspection Record |  |
| --- | --- |
| Software Review Record |  |
| Software Release Note |  |
| Software Requirements Review Meeting Record |  |
| Software Design Review Meeting Record |  |
| Software Verification Review Meeting Record |  |

# Change \ Review History

| Issue | Date | Description |
| --- | --- | --- |
| 9 | 26/03/2025 | Removed reference to SVN and StarTeam(Section 7) |
| 8 | 07/03/2023 | Reviewed and no change. |
| 7 | 17/11/2020 | Seventh Issue - Changed the Process Owner’s name on this document - Changed the name of Global Procedure documents as per current VTMS standards |
| 6 | 03/01/2018 | Sixth Issue - Changed FabWorks to EdCentra - In section 7, Record Retention, SVN details added - Hyperlinks to Reference Documents removed - In Section 4, Measurement and Review, updated the details of Metrics collected - Diagram in section 4.1.9 and section 4.1.10 updated to have the PFP gate names altered to match the convention now adopted in the Vacuum techniques PCP - Footer updated |
| 5 | 11/12/14 | Fifth Issue - In section 5, Form Templates, update Review Meeting Record templates to clarify design checklist and comments/actions list - Updated reference links to other documents |
| 4 | 24/04/13 | Fourth Issue - Add to section 4.1.10 that regular scheduled formal meetings occur to agree inclusion of changes in software releases. - Add to section 4.1.5 that independent testing should occur. - Add to Section 4.1.6 and Software Release Note template in section 5.5 that embedded software releases must be checked through production testing. - Move S3 and E-2 gates in sections 4.1.9 & 4.1.10 so that E-2 precedes beta software release for external customers. Also add deployment step to beta release in diagrams. |
| 3 | 12/12/11 | Third Issue – Requirements, Design and Verification Review Meetings identified in new section 4.1.10. Templates for these reviews added to section 5.5. Project Plan defined in section 4.1.2. |
| 2 | 03/10/11 | Second Issue – Hyperlinks to external documents updated. eCAR changed to FRACAS. |
| 1 | 27/10/09 | First Issue |

# Record Retention

| Record | Retention Period | Location |
| --- | --- | --- |
| All product documentation | 10 years after product ‘end of life’ | Eastbourne project file server |
| All project source code | 10 years after product ‘end of life’ | SVN, GitHub and Azure Repos (migration from SVN to Git and Azure Repos in progress at the time of issuing this document) |